## Summary
VeerNXT Social - Campaign Plan & Costing
Draft for review. Audience: Indian Ex-Service Men (ESM), families and employers. Channels: LinkedIn, X, Instagram, Facebook.
At a glance
Start date | 2026-10-12
End date (last post) | 2026-12-05
Duration (weeks) | 8
Content items (themes) | 16
Total posts across all platforms | 64
Posts per week (all platforms) | 8
Reduction vs posting daily on every platform | 71.43%
Cadence per platform (posts per week)
LinkedIn | 2
X | 2
Instagram | 2
Facebook | 2
Estimated AI generation cost (INR)
| Low | Expected | High
Total campaign | 48.636 | 78.165 | 165.208
Per content item | 3.0398 | 4.8853 | 10.3255
Per post | 0.75994 | 1.2213 | 2.5814
For approval / to confirm
1. Audience wording: the website is written largely for Agniveers, but the social brand rules exclude that word. Decide whether social posts stay ESM/veteran-only.
2. Themes, order and pillars (Themes sheet) - approve, replace or reorder.
3. Claims to verify before posting (last column of the Themes sheet): "Government Approved", SEBI-compliant, NISM-certified, "500+ exams", community and veteran counts.
4. Features not yet live or fully stocked: Legal Aid Cell ("demonstration"), WhatsApp alerts, Rewards catalogue, app-store listings.
5. Start date, posting days and IST posting times; whether all four platforms are needed.
6. Publishing method: currently Mock / Manual; native platform integration and any scheduler are not yet priced.
7. Not costed: paid promotion, staff time, hosting, GST and bank charges.
8. All posts follow brand rules: "Ex-Service Men (ESM)" terminology, no invented facts, statistics or testimonials; every post is reviewed and approved before publishing.
Cost figures are estimates; see Costing and Assumptions sheets for basis and sources.

## Themes
Campaign Themes
Umbrella theme: "Your Second Mission". A journey from awareness to joining. Built from what the VeerNXT site and app actually do. Edit the blue cells; the Schedule updates.
Item # | Week | Phase | Pillar | Theme | Key message (draft) | Where it comes from | Verify before posting
1 | 1 | Awareness | P0 The Second Mission | Your second mission begins here | VeerNXT is a veteran-led platform helping Ex-Service Men (ESM) move into civilian and government careers: jobs, study tools, finance and support in one place. | Site hero and "Why VeerNXT" copy; stakeholder talking points. | "Government of India Approved" (older hero) vs "Aligned" (landing) - use neither until confirmed. "First Defence Reintegration EdTech" needs proof.
2 | 1 | Awareness | P1 Your Skills, Translated | Your service skills are civilian skills | Trade, rank and education translate into a civilian skill profile. Discipline and leadership are only part of the story. | Profiling flow; stakeholder talking points, section 3. | None - no statistics used.
3 | 2 | Discover | P1 Your Skills, Translated | Thirty seconds to your profile | Tell us your education, goals and preferred locations. VeerNXT recommends your best-fit exams and next steps. | How VeerNXT Works: Profile Scan and Mission Assignment steps. | Confirm the "30 seconds" timing against the current profiling flow.
4 | 2 | Discover | P1 Your Skills, Translated | Your Veer Score: know where you stand | One clear picture of your strengths and your best-fit exam matches, so you know where to start. | Stakeholder talking points; Dashboard "Top Exam Matches". | Describe the score in words only; do not quote score numbers.
5 | 3 | Discover | P2 Every Opportunity, One Place | Every new job, one place | New government jobs from 10+ portals in one app, with closed listings removed daily. | Stakeholder talking points, section 2 (jobs scraper). | Confirm current portal count and daily refresh before quoting.
6 | 3 | Discover | P2 Every Opportunity, One Place | Never miss a benefit meant for you | Ex-servicemen quotas, age relaxations and bonus marks are highlighted on each job, so you do not miss what is built for you. | Stakeholder talking points, section 2; eligibility engine. | Keep to ESM benefits; agree wording with the content team so it is accurate per notification.
7 | 4 | Prepare | P3 Prepare to Win | From target job to study plan | Pick a career such as Bank Officer, Railways or State Police and get its syllabus, previous-year papers, guides and quizzes. | Learning Center, Exam Syllabus, PYQ Center, Quiz Center. | Site says "500+ exams"; the catalogue holds more. Reconcile before quoting a number. Only feature exams with content live.
8 | 4 | Prepare | P3 Prepare to Win | Train like it is your PT schedule | Daily tasks, lessons and practice tests, planned like your PT routine. | Workflow step 3 (Training Plan); Today Objective card. | Content coverage varies by state and UT; show exams that are actually populated.
9 | 5 | Career Paths | P4 Beyond Government | Beyond government: the private sector path | A managed route to private-sector roles: a verified service profile, opportunities screened by VeerNXT HR, and a simple "I am interested" or "Not for me". | Private Sector module (home, profile, opportunities). | WhatsApp notifications were still simulated at last status report; do not promise alerts.
10 | 5 | Career Paths | P1 Your Skills, Translated | A CV that speaks civilian | Present your service experience in the terms employers use, with the CV Builder. | CV Builder page. | Check the live CV Builder features before describing them.
11 | 6 | Career Paths | P5 Hire Veterans | For employers: pre-verified veteran talent | The Employer Portal lets employers post requirements and find pre-verified veteran candidates. | Employer portal (onboarding, dashboard, post job, find candidates). | Landing copy says employers contact candidates directly; the Private Sector module is deliberately HR-mediated. Align the wording first.
12 | 6 | Career Paths | P5 Hire Veterans | What a service record tells an employer | Discipline, leadership and teamwork under pressure are demonstrated, not claimed. | Brand voice; general editorial point. | None - no statistics used.
13 | 7 | Secure & Support | P6 Secure Your Future | Plan your separation corpus | Free calculators for SIP, step-up SIP, cost of delay, emergency fund and retirement, to plan before you invest. | Financial Guidance page and calculators. | Add "not investment advice". Claims such as SEBI-compliant or NISM-certified planners need documentary proof.
14 | 7 | Secure & Support | P7 Stand By You | Legal help, organised: the Legal Aid Cell | Describe your situation in plain words; a coordinator organises your documents and connects you with a suitable legal professional. This is not legal advice. | Legal Aid Cell page. | The page still says "demonstration". Confirm it is live before promoting. Sensitive topic: no outcome promises, no case stories.
15 | 8 | Join | P8 Stronger Together | You are not doing this alone | Connect with fellow veterans and mentors, and earn points for using VeerNXT. | Connect & Thrive; Network; Rewards Center. | Do not promote rewards until the catalogue is stocked (it showed empty). Confirm the community-size claim.
16 | 8 | Join | P0 The Second Mission | Start your second mission | Build your profile free and see your best-fit exams and jobs. Available in nine Indian languages. | Languages: English, Hindi, Tamil, Bengali, Marathi, Malayalam, Telugu, Gujarati, Kannada; free-to-start model. | Confirm app-store availability ("coming soon" on landing) and the CTA link.

## Pillars
Content Pillars
Nine pillars, each tied to a real part of the VeerNXT product. Item and post counts come from the Themes and Schedule sheets.
Pillar | What it covers | Main audience | Lead platforms | Content items | Posts
P0 The Second Mission | Brand story: who VeerNXT is, and the invitation to join. | All | Facebook, LinkedIn | 2 | 8
P1 Your Skills, Translated | Career profiling: military trade, rank and education mapped to a civilian skill profile and Veer Score; CV Builder. | ESM, serving personnel planning ahead | LinkedIn, Instagram | 4 | 16
P2 Every Opportunity, One Place | Job aggregation from 10+ portals; ESM quotas, relaxations and bonus marks highlighted; expired jobs removed daily. | ESM job seekers | X, Facebook | 2 | 8
P3 Prepare to Win | Learning Center: syllabus, guides, precis, previous-year papers, mock tests and quizzes for central and state exams; daily training plan. | ESM preparing for government exams | Instagram, Facebook | 2 | 8
P4 Beyond Government | Private Sector module: verified service profile, VeerNXT HR-mediated opportunities, "I am interested" or "Not for me" only. | ESM seeking corporate roles | LinkedIn | 1 | 4
P5 Hire Veterans | Employer Portal: pre-verified veteran talent, requirement posting; the value of service experience at work. | Employers, HR leaders | LinkedIn, X | 2 | 8
P6 Secure Your Future | Financial guidance: calculators (SIP, step-up SIP, cost of delay, emergency fund, retirement), fixed deposits, mutual funds, insurance basics. | ESM with separation corpus, families | Facebook, Instagram | 1 | 4
P7 Stand By You | Legal Aid Cell: guided intake for service, pension and family matters; coordinator connects to a legal professional. Not legal advice. | ESM, families, dependants | Facebook, LinkedIn | 1 | 4
P8 Stronger Together | Community and network, mentors, peer support, rewards points; app available in 9 Indian languages. | ESM, families, mentors | Facebook, Instagram | 1 | 4
Total |  |  |  | 16 | 64
Platform voice: LinkedIn = editorial and insight; X = short and sharp; Instagram = visual and warm; Facebook = conversational and community.

## Schedule
Campaign Schedule
8 weeks, 2 content items per week. Each item is published on all four platforms, staggered across the week (no daily posting). Times are IST. Themes and pillars come from the Themes sheet (change them there).
Post # | Week | Content item # | Theme | Platform | Format | Date | Day | Time (IST) | Day offset (Mon = 0) | Status | Pillar | Phase
1 | 1 | 1 | Your second mission begins here | LinkedIn | Editorial post + image | 2026-10-13 | Tue | 9:30 | 1 | Proposed | P0 The Second Mission | Awareness
2 | 1 | 1 | Your second mission begins here | X | Short post + image | 2026-10-13 | Tue | 10:00 | 1 | Proposed | P0 The Second Mission | Awareness
3 | 1 | 1 | Your second mission begins here | Facebook | Community post + image | 2026-10-14 | Wed | 19:00 | 2 | Proposed | P0 The Second Mission | Awareness
4 | 1 | 1 | Your second mission begins here | Instagram | Image post + caption | 2026-10-15 | Thu | 18:00 | 3 | Proposed | P0 The Second Mission | Awareness
5 | 1 | 2 | Your service skills are civilian skills | X | Short post + image | 2026-10-16 | Fri | 10:00 | 4 | Proposed | P1 Your Skills, Translated | Awareness
6 | 1 | 2 | Your service skills are civilian skills | LinkedIn | Editorial post + image | 2026-10-16 | Fri | 12:30 | 4 | Proposed | P1 Your Skills, Translated | Awareness
7 | 1 | 2 | Your service skills are civilian skills | Instagram | Image post + caption | 2026-10-17 | Sat | 18:00 | 5 | Proposed | P1 Your Skills, Translated | Awareness
8 | 1 | 2 | Your service skills are civilian skills | Facebook | Community post + image | 2026-10-17 | Sat | 19:00 | 5 | Proposed | P1 Your Skills, Translated | Awareness
9 | 2 | 3 | Thirty seconds to your profile | LinkedIn | Editorial post + image | 2026-10-20 | Tue | 9:30 | 1 | Proposed | P1 Your Skills, Translated | Discover
10 | 2 | 3 | Thirty seconds to your profile | X | Short post + image | 2026-10-20 | Tue | 10:00 | 1 | Proposed | P1 Your Skills, Translated | Discover
11 | 2 | 3 | Thirty seconds to your profile | Facebook | Community post + image | 2026-10-21 | Wed | 19:00 | 2 | Proposed | P1 Your Skills, Translated | Discover
12 | 2 | 3 | Thirty seconds to your profile | Instagram | Image post + caption | 2026-10-22 | Thu | 18:00 | 3 | Proposed | P1 Your Skills, Translated | Discover
13 | 2 | 4 | Your Veer Score: know where you stand | X | Short post + image | 2026-10-23 | Fri | 10:00 | 4 | Proposed | P1 Your Skills, Translated | Discover
14 | 2 | 4 | Your Veer Score: know where you stand | LinkedIn | Editorial post + image | 2026-10-23 | Fri | 12:30 | 4 | Proposed | P1 Your Skills, Translated | Discover
15 | 2 | 4 | Your Veer Score: know where you stand | Instagram | Image post + caption | 2026-10-24 | Sat | 18:00 | 5 | Proposed | P1 Your Skills, Translated | Discover
16 | 2 | 4 | Your Veer Score: know where you stand | Facebook | Community post + image | 2026-10-24 | Sat | 19:00 | 5 | Proposed | P1 Your Skills, Translated | Discover
17 | 3 | 5 | Every new job, one place | LinkedIn | Editorial post + image | 2026-10-27 | Tue | 9:30 | 1 | Proposed | P2 Every Opportunity, One Place | Discover
18 | 3 | 5 | Every new job, one place | X | Short post + image | 2026-10-27 | Tue | 10:00 | 1 | Proposed | P2 Every Opportunity, One Place | Discover
19 | 3 | 5 | Every new job, one place | Facebook | Community post + image | 2026-10-28 | Wed | 19:00 | 2 | Proposed | P2 Every Opportunity, One Place | Discover
20 | 3 | 5 | Every new job, one place | Instagram | Image post + caption | 2026-10-29 | Thu | 18:00 | 3 | Proposed | P2 Every Opportunity, One Place | Discover
21 | 3 | 6 | Never miss a benefit meant for you | X | Short post + image | 2026-10-30 | Fri | 10:00 | 4 | Proposed | P2 Every Opportunity, One Place | Discover
22 | 3 | 6 | Never miss a benefit meant for you | LinkedIn | Editorial post + image | 2026-10-30 | Fri | 12:30 | 4 | Proposed | P2 Every Opportunity, One Place | Discover
23 | 3 | 6 | Never miss a benefit meant for you | Instagram | Image post + caption | 2026-10-31 | Sat | 18:00 | 5 | Proposed | P2 Every Opportunity, One Place | Discover
24 | 3 | 6 | Never miss a benefit meant for you | Facebook | Community post + image | 2026-10-31 | Sat | 19:00 | 5 | Proposed | P2 Every Opportunity, One Place | Discover
25 | 4 | 7 | From target job to study plan | LinkedIn | Editorial post + image | 2026-11-03 | Tue | 9:30 | 1 | Proposed | P3 Prepare to Win | Prepare
26 | 4 | 7 | From target job to study plan | X | Short post + image | 2026-11-03 | Tue | 10:00 | 1 | Proposed | P3 Prepare to Win | Prepare
27 | 4 | 7 | From target job to study plan | Facebook | Community post + image | 2026-11-04 | Wed | 19:00 | 2 | Proposed | P3 Prepare to Win | Prepare
28 | 4 | 7 | From target job to study plan | Instagram | Image post + caption | 2026-11-05 | Thu | 18:00 | 3 | Proposed | P3 Prepare to Win | Prepare
29 | 4 | 8 | Train like it is your PT schedule | X | Short post + image | 2026-11-06 | Fri | 10:00 | 4 | Proposed | P3 Prepare to Win | Prepare
30 | 4 | 8 | Train like it is your PT schedule | LinkedIn | Editorial post + image | 2026-11-06 | Fri | 12:30 | 4 | Proposed | P3 Prepare to Win | Prepare
31 | 4 | 8 | Train like it is your PT schedule | Instagram | Image post + caption | 2026-11-07 | Sat | 18:00 | 5 | Proposed | P3 Prepare to Win | Prepare
32 | 4 | 8 | Train like it is your PT schedule | Facebook | Community post + image | 2026-11-07 | Sat | 19:00 | 5 | Proposed | P3 Prepare to Win | Prepare
33 | 5 | 9 | Beyond government: the private sector path | LinkedIn | Editorial post + image | 2026-11-10 | Tue | 9:30 | 1 | Proposed | P4 Beyond Government | Career Paths
34 | 5 | 9 | Beyond government: the private sector path | X | Short post + image | 2026-11-10 | Tue | 10:00 | 1 | Proposed | P4 Beyond Government | Career Paths
35 | 5 | 9 | Beyond government: the private sector path | Facebook | Community post + image | 2026-11-11 | Wed | 19:00 | 2 | Proposed | P4 Beyond Government | Career Paths
36 | 5 | 9 | Beyond government: the private sector path | Instagram | Image post + caption | 2026-11-12 | Thu | 18:00 | 3 | Proposed | P4 Beyond Government | Career Paths
37 | 5 | 10 | A CV that speaks civilian | X | Short post + image | 2026-11-13 | Fri | 10:00 | 4 | Proposed | P1 Your Skills, Translated | Career Paths
38 | 5 | 10 | A CV that speaks civilian | LinkedIn | Editorial post + image | 2026-11-13 | Fri | 12:30 | 4 | Proposed | P1 Your Skills, Translated | Career Paths
39 | 5 | 10 | A CV that speaks civilian | Instagram | Image post + caption | 2026-11-14 | Sat | 18:00 | 5 | Proposed | P1 Your Skills, Translated | Career Paths
40 | 5 | 10 | A CV that speaks civilian | Facebook | Community post + image | 2026-11-14 | Sat | 19:00 | 5 | Proposed | P1 Your Skills, Translated | Career Paths
41 | 6 | 11 | For employers: pre-verified veteran talent | LinkedIn | Editorial post + image | 2026-11-17 | Tue | 9:30 | 1 | Proposed | P5 Hire Veterans | Career Paths
42 | 6 | 11 | For employers: pre-verified veteran talent | X | Short post + image | 2026-11-17 | Tue | 10:00 | 1 | Proposed | P5 Hire Veterans | Career Paths
43 | 6 | 11 | For employers: pre-verified veteran talent | Facebook | Community post + image | 2026-11-18 | Wed | 19:00 | 2 | Proposed | P5 Hire Veterans | Career Paths
44 | 6 | 11 | For employers: pre-verified veteran talent | Instagram | Image post + caption | 2026-11-19 | Thu | 18:00 | 3 | Proposed | P5 Hire Veterans | Career Paths
45 | 6 | 12 | What a service record tells an employer | X | Short post + image | 2026-11-20 | Fri | 10:00 | 4 | Proposed | P5 Hire Veterans | Career Paths
46 | 6 | 12 | What a service record tells an employer | LinkedIn | Editorial post + image | 2026-11-20 | Fri | 12:30 | 4 | Proposed | P5 Hire Veterans | Career Paths
47 | 6 | 12 | What a service record tells an employer | Instagram | Image post + caption | 2026-11-21 | Sat | 18:00 | 5 | Proposed | P5 Hire Veterans | Career Paths
48 | 6 | 12 | What a service record tells an employer | Facebook | Community post + image | 2026-11-21 | Sat | 19:00 | 5 | Proposed | P5 Hire Veterans | Career Paths
49 | 7 | 13 | Plan your separation corpus | LinkedIn | Editorial post + image | 2026-11-24 | Tue | 9:30 | 1 | Proposed | P6 Secure Your Future | Secure & Support
50 | 7 | 13 | Plan your separation corpus | X | Short post + image | 2026-11-24 | Tue | 10:00 | 1 | Proposed | P6 Secure Your Future | Secure & Support
51 | 7 | 13 | Plan your separation corpus | Facebook | Community post + image | 2026-11-25 | Wed | 19:00 | 2 | Proposed | P6 Secure Your Future | Secure & Support
52 | 7 | 13 | Plan your separation corpus | Instagram | Image post + caption | 2026-11-26 | Thu | 18:00 | 3 | Proposed | P6 Secure Your Future | Secure & Support
53 | 7 | 14 | Legal help, organised: the Legal Aid Cell | X | Short post + image | 2026-11-27 | Fri | 10:00 | 4 | Proposed | P7 Stand By You | Secure & Support
54 | 7 | 14 | Legal help, organised: the Legal Aid Cell | LinkedIn | Editorial post + image | 2026-11-27 | Fri | 12:30 | 4 | Proposed | P7 Stand By You | Secure & Support
55 | 7 | 14 | Legal help, organised: the Legal Aid Cell | Instagram | Image post + caption | 2026-11-28 | Sat | 18:00 | 5 | Proposed | P7 Stand By You | Secure & Support
56 | 7 | 14 | Legal help, organised: the Legal Aid Cell | Facebook | Community post + image | 2026-11-28 | Sat | 19:00 | 5 | Proposed | P7 Stand By You | Secure & Support
57 | 8 | 15 | You are not doing this alone | LinkedIn | Editorial post + image | 2026-12-01 | Tue | 9:30 | 1 | Proposed | P8 Stronger Together | Join
58 | 8 | 15 | You are not doing this alone | X | Short post + image | 2026-12-01 | Tue | 10:00 | 1 | Proposed | P8 Stronger Together | Join
59 | 8 | 15 | You are not doing this alone | Facebook | Community post + image | 2026-12-02 | Wed | 19:00 | 2 | Proposed | P8 Stronger Together | Join
60 | 8 | 15 | You are not doing this alone | Instagram | Image post + caption | 2026-12-03 | Thu | 18:00 | 3 | Proposed | P8 Stronger Together | Join
61 | 8 | 16 | Start your second mission | X | Short post + image | 2026-12-04 | Fri | 10:00 | 4 | Proposed | P0 The Second Mission | Join
62 | 8 | 16 | Start your second mission | LinkedIn | Editorial post + image | 2026-12-04 | Fri | 12:30 | 4 | Proposed | P0 The Second Mission | Join
63 | 8 | 16 | Start your second mission | Instagram | Image post + caption | 2026-12-05 | Sat | 18:00 | 5 | Proposed | P0 The Second Mission | Join
64 | 8 | 16 | Start your second mission | Facebook | Community post + image | 2026-12-05 | Sat | 19:00 | 5 | Proposed | P0 The Second Mission | Join
Formulas:
Date = Assumptions!$B4+([Week]-1)*7+[Day offset (Mon = 0)]

## Cadence
Posting Cadence
Posts per platform per week, counted from the Schedule sheet.
Platform | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Total | Per week
LinkedIn | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 16 | 2
X | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 16 | 2
Instagram | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 16 | 2
Facebook | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 16 | 2
All platforms | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 64 | 8
Comparison with posting daily on every platform
Posts if daily on all 4 platforms | Wk 1: 224
Posts in this plan | Wk 1: 64
Reduction vs daily | Wk 1: 71.43%

## Costing
Campaign Costing
AI content generation only (OpenAI API). Low / Expected / High cases. USD and INR. All figures are estimates - see Assumptions.
Line | Low (USD) | Expected (USD) | High (USD) | Low (INR) | Expected (INR) | High (INR)
Content items to generate | 16 | 16 | 16
Posts to publish | 64 | 64 | 64
Text generation (4 platforms per item) | 0.192 | 0.24 | 0.32 | 18.528 | 23.16 | 30.88
Image generation (1 image per item) | 0.208 | 0.28 | 0.48 | 20.072 | 27.02 | 46.32
Refinement edits by the team | 0.064 | 0.16 | 0.512 | 6.176 | 15.44 | 49.408
Regeneration allowance after review | 0.04 | 0.13 | 0.4 | 3.86 | 12.545 | 38.6
AI generation subtotal | 0.504 | 0.81 | 1.712 | 48.636 | 78.165 | 165.208
Hosting / third-party tools (not included unless entered) | 0 | 0 | 0 | 0 | 0 | 0
TOTAL CAMPAIGN COST | 0.504 | 0.81 | 1.712 | 48.636 | 78.165 | 165.208
Cost per content item | 0.0315 | 0.050625 | 0.107 | 3.0398 | 4.8853 | 10.3255
Cost per post | 0.007875 | 0.012656 | 0.02675 | 0.75994 | 1.2213 | 2.5814
Notes
Publishing is not costed: the app currently publishes via Mock/Manual providers (no per-post fee). Native LinkedIn / X / Meta API integration and any scheduler such as Buffer are not yet priced.
Excluded: paid promotion / ad spend, staff time for review and approval, GST, bank foreign-transaction fees, and hosting unless entered in Assumptions.
Rates and token counts are estimates from public price pages and assumed token volumes; check the OpenAI usage dashboard for actual spend.

## Assumptions
Assumptions & Inputs
Blue cells are inputs - change them and every sheet recalculates. Yellow = key assumptions to confirm.
General
Campaign start date (a Monday) | 2026-10-12 |  |  | Proposed. Change to the approved launch date.
USD to INR exchange rate | 96.5 |  |  | Approx. rate at 30 Sep 2026 from a web search (pluang.com currency converter); not a live rate. Update before final approval.
Hosting / third-party tools (INR per month) | 0 |  |  | NOT INCLUDED - to confirm (e.g. Vercel, Supabase, Buffer). Enter monthly amount if applicable.
Campaign length (months, derived) | 1.8462
Per-unit cost inputs
Item | Low | Expected | High | Basis
Text generation, USD per content item (all 4 platforms, gpt-4o) | 0.012 | 0.015 | 0.02 | gpt-4o at $2.50/1M input and $10/1M output tokens (analyticsvidhya.com). Assumes ~1,000 tokens in, ~1,200 out. Estimate.
Image, USD per image (gpt-image-2.5-flare, medium quality) | 0.013 | 0.0175 | 0.03 | Flare: $30/1M image-output tokens; ~439 tokens for 1024x1024 medium = ~$0.013 (openrouter.ai). Landscape 1536x1024 costs more. Estimate.
Refinement call, USD each (short gpt-4o edit) | 0.004 | 0.005 | 0.008 | Estimate: short prompt and single-post response.
Refinements per content item (count) | 1 | 2 | 4 | Editor "shorten / hook / CTA" style edits by the team. Assumption.
Regeneration allowance (% of items re-generated) | 10% | 25% | 50% | Items re-run in full (text + image) after review feedback. Assumption.